## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | Data ingestion & preprocessing | Must |  | Sandhya | Completed
Sprint 2 | Sprint 2 | US-002 | Knowledge graph creation using Neo4j | Must |  | Sandhya | Completed
Sprint 3 | Sprint 3 | US-003 | Semantic search using TF-IDF | Must |  | Sandhya | Completed
Sprint 4 | Sprint 4 | US-004 | Streamlit dashboard UI | Must |  | Sandhya | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Data ingestion pipeline | 2026-02-01 | 4/Feb/26 | Sandhya | coding | completed | 5
US-002 | 2 | Knowledge graph creation | 16/Feb/26 | 21/Feb/26 | Sandhya | coding | completed | 8
US-003 | 3 | Semantic search TF-IDF | 2026-03-15 | 2026-03-25 | Sandhya | coding | completed | 7
US-004 | 4 | Streamlit dashboard | 21/Mar/26 | 2026-04-01 | Sandhya | design & coding | completed | 6
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Understanding dataset | Explored dataset
Sprint 2 | Day 5 | Graph modeling confusion | Resolved using docs
Sprint 3 | Day 10 | Model selection issue | Tested multiple models
Sprint 4 | Day 15 | UI integration issues | Fixed bugs and improved UI

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-01 | 2026-02-04 | Sandhya | Better planning | Avoid assumptions | Team discussion | Used mentor guidance
2 | Sprint 2 | 2026-02-16 | 2026-02-21 | Sandhya | Proper dataset selection | Random selection | Validation | Improved selection
3 | Sprint 3 | 2026-03-15 | 2026-03-25 | Sandhya | Model testing | Wrong assumptions | Experimentation | Better model chosen
4 | Sprint 4 | 2026-03-21 | 2026-04-01 | Sandhya | UI integration | Rushing tasks | Focus | Stable dashboard built
5
6
7